# Technical Specification - Asset Commissioning and Transition to Operation - Templates

This document contains templates to assist Service Providers in meeting the requirements of D001440 Technical Specification – Asset Commissioning and Transition to Operation

Table of Contents

Revision details	3

Introduction	3

Copyright	3

1.	Commissioning Plan Templates	4

2.	Cut-over Plan Templates	25

3.	Commissioning Risk Assessment Template	33

4.	Monitoring and Measuring Device (MMD) Register Template	35

5.	O&M Manual Template	35

Ownership	50

Ownership	50

Change history	50

# Revision details

| Version No. | Clause | Description of revision |
| --- | --- | --- |
| A | All | New Document containing non-asset specific templates from D0001440 in editable format for use. |

# Introduction

This document contains information removed from D0001440 to be provided in an editable format for use by Service Providers.

Sydney Water makes no warranties, express or implied, that compliance with the contents of these Templates shall be sufficient to ensure safe systems or work or operation.

It is the user’s sole responsibility to ensure that the copy of the Templates is the current version as in use by Sydney Water.

Sydney Water accepts no liability whatsoever in relation to the use of these Templates by any party, and Sydney Water excludes any liability which arises in any manner by the use of these Templates.

For the purpose of these Templates “Sydney Water” is the nominated person or organisation that has written authority to act on Sydney Water’s behalf.

This document is uncontrolled once printed or downloaded.

# Copyright

The information in this document is protected by Copyright and no part of this document may be reproduced, altered, stored or transmitted by any person without the prior consent of Sydney Water.

Commissioning Plan Template

Introduction	5

Project Description	5

Project Critical Data	5

Document Objectives	5

Commissioning Team	6

Roles and Responsibilities	6

Team Structure	6

Communication Protocols and Stakeholder Matrix	6

Managing Safety During Commissioning	8

Commissioning Approach	9

Commissioning Process	9

Commissioning work lots & staging	9

Work Lot Methodologies	10

Work Lot XX – Work lot name	10

Work lot description & boundaries	10

Work lot references	10

Work lot pre-requisites and input requirements	10

Work lot third party inputs	10

Work lot commissioning methodology	11

Work lot testing and monitoring requirements	11

Work lot acceptance criteria	12

Process Proving	13

Pre-requisites and input requirements	13

Contacts and call outs	13

Monitoring during process proving	13

Testing and sampling during process proving	14

Process proving completion & acceptance criteria	14

Operational Readiness & handover	14

Contingency Plan	15

Operations and maintenance training	16

Definitions	17

Attachments	17

Ownership	18

Change History	18

Appendix 1 – Typical commissioning activities by discipline and commissioning phase	19

Commissioning inspection and test plan (ITP) register	19

Commissioning ITPs	19

Commissioning inspection and test checklists (ITCs)	19

Typical Pre-commissioning activities	20

Pre-commissioning electrical activities	20

Pre-commissioning HV electrical activities	20

Pre-commissioning mechanical activities	20

Typical Dry-commissioning activities	21

Dry-commissioning electrical activities	21

Dry-commissioning controls and instrumentation activities	21

Dry-commissioning mechanical activities	22

Dry-commissioning electrical-mechanical activities	23

# Introduction

## Project Description

[Do not type here. This is instructional text.

Mandatory. Explain briefly the background of the project/activity/upgrade. Keep to a very key and simple description]

[Enter text]

## Project Critical Data

[Do not type here. This is instructional text.

Mandatory. Using the table below summarise the key critical system design criteria, and the source of the information. For larger systems keep to system level performance, rather than individual asset (this will be covered later. Delete example text in yellow.]

| Work Lot | Description | Design Criteria | Relevant Design Document |
| --- | --- | --- | --- |
| 1.1 | WAS Thickening System | 4% DS @ 25 KL/hr | Design Report |
| [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] |

## Document Objectives

[Do not type here. This is instructional text.

Mandatory. Summarise the key objectives of the document. Text in yellow is example text only.

This plan describes the approach to undertaking commissioning activities for this project. Detail activities, tests and witness/hold points will be contained within the commissioning ITPs and ITCs.

This is intended to be a live document that will be revised and updated to align with site conditions, and operational needs.

The objectives of this document are to:

- Describe the commissioning procedure and methodology

- Define criteria required and the documents required to have the equipment systems successfully placed into operation.

- Define commissioning pre-requisites.

- Provide standard commissioning procedures.

- Define the inspections and tests required at each stage

- Complete and sign off all required commissioning and handover deliverables.

# Commissioning Team

## Roles and Responsibilities

[Do not type here. This is instructional text.

Mandatory. Update the highlighted text as required to reflect the commissioning R&R for the specific project.

The Commissioning Team will be a multi-skilled team utilising a range of resources from Suppliers, Customer Delivery, Maintenance, Design and Construction. The team structure is presented in the figure below.

The Service Provider Commissioning Lead is responsible for coordinating all commissioning activities and overseeing delivery of commissioning (inclusive of process proving and optimisation) in accordance with this commissioning plan, and in compliance with the project scope and technical specifications.

Specific roles and responsibilities between different parties in commissioning will be as per the RACI in D001440 Technical Specification – Asset Commissioning and Transition to Operation.

## Team Structure

[Do not type here. This is instructional text.

Mandatory. Provide a team structure diagram for the Commissioning Team. This should include key stakeholders, and 3rd parties involved in the commissioning process.]

## Communication Protocols and Stakeholder Matrix

The following communication frequency and protocols will be followed for the commissioning phase;

| Item | Description | Format | Frequency |
| --- | --- | --- | --- |
|  | Commissioning Kick Off & Risk Assessment | Meeting | Prior to Pre-Commissioning |
|  | [Enter Text] | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] | [Enter Text] |

The Service Provider should work with the Sydney Water Project Manager to identify the relevant Stakeholders responsible for the sign offs listed in the RACI for the specific project and update the Stakeholder Matrix below.

| Sign off Type/Event | Sydney Water (SW) sign-off required? | SW Responsible Role | SW responsible person (current) | Comment |
| --- | --- | --- | --- | --- |
| Cut over plan approval - HOLD POINT | Yes | Senior Process Engineer | Chris Raynor | All communications should be via SW PE |
| Commissioning plan approval - HOLD POINT | Yes | Operational Acceptance & Asset Integration Specialist | Juan Medellin Sarmiento & Samuel Liu | All communications should be via SW PE |
| Factory Acceptance Tests (FAT) on manufactured equipment | Where req'd | Operational Acceptance Specialist | Juan Medellin Sarmiento | FAT reports are reviewed and approved through ineight All communications should be via SW PE |
| FAT on software - HOLD POINT | Yes | Senior Process Engineer/ Process Controller | Chris Raynor/ Nicole Schroder | All communications should be via SW PE |
| Site Acceptance Tests (SAT) - Equipment | Where req'd | Operational Acceptance Specialist & Asset Integration Specialist | Juan Medellin Sarmiento & Samuel Liu | All communications should be via SW PE |
| Site Acceptance Tests (SAT) - Software | Where req'd | Senior Process Engineer/ Process Controller & Operational Acceptance Specialist | Chris Raynor/ Nicole Schroder & Juan Medellin Sarmiento | All communications should be via SW PE |
| Software download plan | Yes | SCADA Config & Test Eng & Process Controller | Anushree Deshpande & Nicole Schroder | All communications should be via SW PE |
| Installation Completion Report - HOLD POINT | Yes | Operational Acceptance Specialist & Asset Integration Specialist | Juan Medellin Sarmiento & Samuel Liu | IT should be captured in the installation ITPs All communications should be via SW PE |
| Acceptance of commissioning date (10 days notice) | Yes | Operational Acceptance Specialist & Asset Integration Specialist | Juan Medellin Sarmiento & Samuel Liu | All communications should be via SW PE |

## Managing Safety During Commissioning

[Do not type here. This is instructional text. Mandatory. Explain how safety will be managed throughout commissioning activities. This may include risk assessments, communication, specific training requirements for team members, permits to work, exclusion zones etc.

[Enter text]

# Commissioning Approach

[Do not type here. This is instructional text.

Mandatory. This section is to summarise the high-level approach to how commissioning will be conducted. The detail for specific commissioning work Lots and packages will be covered in later sections of the document. No text required under this heading, only under the sub headings.]

## Commissioning Process

[Do not type here. This is instructional text. Mandatory. Update the highlighted text as required to reflect the commissioning process being adopted.]

Commissioning will be undertaken in accordance with the standard process contained within the D001440 Technical Specification – Asset Commissioning and Transition to Operation.

## Commissioning work lots & staging

[Do not type here. This is instructional text.

Mandatory. This section should clearly articulate how commissioning will be approached for the works. It is recommended to use a diagram, or table to define the breakdown and interface between work lots and temporary works as required. See example text and diagram below.]

The System Commissioning process will be structured around a Commissioning Sub-System approach. Each Sub-System will be defined as a Commissioning Work Lot. The Commissioning Work Lots will be defined in a logical manner, based around the operational requirements of the site and the Construction Schedule. Defining the Commissioning Work Lots can also assist in defining the Construction schedule. Commissioning ITPs include PIDs and details of the specific individual assets to be commissioned within each work lot.

The diagram below identifies the commissioning work lot packages and their respective dependencies. Each green box represents an ‘Operationally Ready” milestone.

# Work Lot Methodologies

## Work Lot XX – Work lot name

### Work lot description & boundaries

[Do not type here. This is instructional text. Mandatory. Provide a brief (one paragraph) description of the work lot, and its boundaries] [This entire Section will be repeated for each respective work lot]

[Enter text]

### Work lot references

[Do not type here. This is instructional text. Mandatory. In the table below list the key references to this work lot. This does not have to be exhaustive and be realistic about the actual documents that will influence the commissioning activities (P&IDs, ITPs, FDS, PEFD etc)].

| Item | Document No. | Description |
| --- | --- | --- |
|  | ITP-001 | Switchboard FAT ITP |
|  | [Enter Doc. No.] | [Enter Text] |
|  | [Enter Doc. No.] | [Enter Text] |
|  | [Enter Doc. No.] | [Enter Text] |

### Work lot pre-requisites and input requirements

[Do not type here. This is instructional text.

Mandatory. State the inputs and/or pre-requisites required for commissioning of this work lot to begin. It may include cutovers, other construction stages, construction signoffs, or other commissioning work lot completion.]

| Item | Description | Requirement |  |
| --- | --- | --- | --- |
|  | FAT Completed |  | ITP-001 Signed Off. |  |
|  | Defects walk conducted |  | No ‘Major’ Defects. |  |
|  | [Enter Text] |  | [Enter Text] |  |
|  | [Enter Text] |  | [Enter Text] |  |
|  | [Enter Text] |  | [Enter Text] |  |

### Work lot third party inputs

[Do not type here. This is instructional text.

Optional. As applicable – delete sub heading if not relevant. This section is for the listing of any specific requirements or involvement by 3rd Parties – Suppliers, certifiers, approvers etc.]

| Item | Provider | Activities |
| --- | --- | --- |
|  | XYZ Supplier | Commissioning Assistance Installation inspection. |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |

### Work lot commissioning methodology

[Do not type here. This is instructional text.

Mandatory. Explain clearly (preferably with a diagram) the methodology and process for the commissioning activities for this work lot. Dependent on complexity this may be at an asset or sub system level.]

| Item | Activity | Comments |
| --- | --- | --- |
|  | Factory Acceptance Test Switchboard |  |
|  | Complete Un-energised Pre-Commissioning Tests | ITP-123 |
|  | Notice of energisation |  |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |

### Work lot testing and monitoring requirements

[Do not type here. This is instructional text. Mandatory. In the table below, detail key test/monitoring parameters specific to the work lot performance testing. Often these details will be found in the design report or needs specification.]

| Item | Parameter | Unit | Performance Requirement | Test Method | Frequency |
| --- | --- | --- | --- | --- | --- |
|  | Feed Concentration | % DS | 0.4 to 0.8 | Sample | 3 per RDT train, per day |
|  | Outlet Sludge TSR | % DS | 4.0 | Sample | 3 per RDT train, per day |
|  | Feed Rate (Peak) | kL/Hr | 88 | Online | Continuous |
|  | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] |

### Work lot acceptance criteria

[Do not type here. This is instructional text. Mandatory. In the table below, summarise the key criteria for acceptance of the work lot. This includes length of operational testing, tolerances on performance tests, ITP completion requirements.]

| Item | Description | Requirement | Comments |
| --- | --- | --- | --- |
|  | Pass Operational Test | 48 hours | Submit Data Portal Workflow |
|  | ITPs Signed Off | ITP-000, 001, 002 | Signed Off. |
|  | Interim Operating Procedure Training | Training and call outs provided |  |
|  | [Enter Text] | [Enter Text] | [Enter Text] |

# Process Proving

## Pre-requisites and input requirements

[Do not type here. This is instructional text. Mandatory. In the table below, summarise the key pre-requisites to commencing the proving period for the full system.]

| Item | Description | Requirement |
| --- | --- | --- |
|  | Work Lots Operationally Ready |  |
|  | Training Completed |  |
|  | Defects Walks Conducted | No ‘Major’ Defects. |
|  | Proving Kick-Off Meeting Held, | Operations approve Commencement. |
|  | Operations Monitoring Log Provided |  |
|  | Operations Daily Checklist Provided |  |
|  | Updated Call Out Contacts |  |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |
|  | [Enter Text] | [Enter Text] |

## Contacts and call outs

| Description | Requirement |
| --- | --- |
| Engineering Support and coordination | [Enter Name] [Enter Mobile Number] |
| Construction Project Manager | [Enter Name] [Enter Mobile Number] |
| Mechanical Support | [Enter Name] [Enter Mobile Number] |
| Electrical Support | [Enter Name] [Enter Mobile Number] |
| [Enter Text] | [Enter Name] [Enter Mobile Number] |

## Monitoring during process proving

[Do not type here. This is instructional text. Mandatory. In this section, summarise what monitoring will be undertaken during the proving period. Detailed sampling and testing will be summarised in the next section.]

The following information will be recorded during proving to ensure performance may be fully analysed and understood.

Alarm Logs from SCADA

Daily checklists and comments log from operations (including call outs)

Consumption of consumables including power, chemicals, and water.

Sampling and testing results from online instrumentation

Sampling and testing results from accredited lab services.

The information will be consolidated into a single report that will provided to project stakeholders weekly.

## Testing and sampling during process proving

[Do not type here. This is instructional text.

Mandatory. All required sampling and testing requirements should be included here, to make it clear to the reader what has been considered, this may include process parameters, chemical / water / power consumption. If this is large, or a detailed sampling plan is required, consider including as an appendix.]

| Item | Parameter | Unit | Performance Requirement | Test Method | Frequency |
| --- | --- | --- | --- | --- | --- |
|  | Outlet Sludge TSR | % DS | 4.0 | Sample | 3 per RDT train, per day |
|  | Feed Rate (Peak) | kL/Hr | 88 | Online | Continuous |
|  | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] |

## Process proving completion & acceptance criteria

[Do not type here. This is instructional text. Mandatory. In the table below, summarise the key criteria for acceptance of the proving period. This includes length of proving, tolerances on performance tests, ITP completion requirements.]

| Item | Description | Requirement | Comments |
| --- | --- | --- | --- |
|  | Pass Proving Period | 14 Calendar Days |  |
|  | ITPs Signed Off | ITP-000, 001, 002 | Signed Off. |
|  | Commissioning Report Endorsed |  |  |
|  | [Enter Text] | [Enter Text] | [Enter Text] |

## Operational Readiness & handover

The Service Provider should propose here if they are seeking Operational Readiness prior to Handover for any commissioning worklots referencing the requirements of Appendix 4 Operational Readiness Checklist of D0001440.

Project Handover will be undertaken using Sydney Water’s Data Portal handover process, and Appendix 5 Handover checklist of D0001440.

Handover is subject to the requirements of Section 12 of the “Asset Commissioning and Transition to Operation” specification being met.

# Contingency Plan

[Do not type here. This is instructional text.

Optional. Define any critical contingency that may be required in the delivery of commissioning. This must be covered either in this document, or in the Cutover Plan.]

# Operations and maintenance training

[Do not type here. This is instructional text. Mandatory. Define at a high level all the training to be conducted as part of the commissioning. Details of each individual training session to be proposed]

| Item | Description | Led By | Sessions | Attendee Groups | Length |
| --- | --- | --- | --- | --- | --- |
|  | Overview Training | Commissioning Lead | 1 per Team | Operators OM Controller | 2 hours |
|  | Software Operations | SCADA Engineer | 2 | Reliability Engineers Operators | 2 hours |
|  | Process Training | Process Designer | 1 per Team | M&E Leading Hand Reliability Engineers | 4 hours |
|  | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] | [Enter Text] |

# Definitions

[Do not type here. This is instructional text.

Mandatory. Define all key terms and acronyms that are particular to the plan. Do not include terms that are not mentioned in the document.]

| Term | Definition | Source |
| --- | --- | --- |
| [Enter term] | [Enter definition] | [Enter source] |
| [Enter term] | [Enter definition (and further rows as needed)] | [Enter source] |

## Attachments

[Do not type here. This is instructional text.

If relevant, list any attachments to support this procedure. This should Include:

-ITP Register

-Commissioning Schedule

-MMD Register

-Commissioning Risk Assessment (but after performing it with stakeholders)]

| Attachment | Title |
| --- | --- |
| 1 | [Enter text] |
| 2 | [Enter text (and further rows as needed)] |

# Ownership

[Do not type here. This is instructional text.

Mandatory. Insert details of the Group that owns the procedure as well as the as the position title of owner and author.]

| Role | Title |
| --- | --- |
| Group | [Enter text] |
| Owner | [Enter position title] |
| Author | [Enter name and position title] |

## Change History

[Do not type here. This is instructional text.

Mandatory. Insert details of the latest review or changes made to the document. Every time a plan is updated, it must be reissued. Documents will not be accepted without internal review.

List the latest version at the top of the table. Add a new version row by clicking the ‘Add Version’ button (far left of the ‘Home’ tab). To record previous versions type in the oldest version first and click ‘Add Version’ to add each subsequent version.]

| Version | Issue Date | Approved by | Brief description of change and consultation |
| --- | --- | --- | --- |
| V1 | 7/08/2026 | [Enter name and position title] | New document |

# Appendix 1 – Typical commissioning activities by discipline and commissioning phase

[Do not type here. This is instructional text.

This attachment is provided to help Service Providers develop ITPs/ITCs at each phase of the commissioning process. These activities are provided as a guide only. This appendix should be deleted once the appropriate ITPs/ITCS have been developed]

Detailed ITPs and inspection and test check sheets (ITCs) should be developed by the Service Provider in support of the Commissioning Plan, incorporating identification, recording and verification of:

- all relevant asset information required for entry into the SWC technical asset register (TAR)

- all civil, structural, mechanical, electrical, process and control (software) checks necessary for testing, commissioning, and operation of the facility

- all key testing and commissioning activities as identified in the prepared procedures and methodologies

- all performance targets and project objectives as per the requirements of the Contract

- all equipment supplier recommended checks and tests

- the corresponding acceptance criteria that the Service Provider must use for establishing the conformance of the Works with the requirements of the Contract

- all hold, witness, or surveillance points as per the requirements of the Contract, nominated by the OA Team or otherwise nominated by the Service Provider.

## Commissioning inspection and test plan (ITP) register

The Commissioning ITP Register is a high-level document breaking down and identifying individual work elements within the overall commissioning works.

The Commissioning ITP Register will identify the commissioning work lots to be developed and their associated Commissioning ITPs and ITCs.

## Commissioning ITPs

Specific Commissioning ITP’s will be prepared for each commissioning sub-system on a sequential basis.

ITPs define system elements that are to be tested, inspection and test routines that will be employed, acceptance criteria, and verification records to be produced or provided.

Hold and witness points will be defined in the ITP to satisfy the requirements in the specifications.

Once all specified test routines have been successfully completed and documentary evidence approved, then the associated commissioning activity can be approved by the Commissioning Manager.

A guideline and checklist for ITP development is available from SWC.

## Commissioning inspection and test checklists (ITCs)

ITC checklists are to be produced which define specific inspection and test routines with sufficient space to enable record test results for each commissioning procedure, and reference the acceptance criteria as required by the relevant standards

Each asset must be accompanied by ITCs which define set points, checks and other verification records as required to ensure reliable operation. Relevant ITCs will be referenced from the ITP.

## Typical Pre-commissioning activities

### Pre-commissioning electrical activities

Electrical equipment checks and testing will include but not limited to the following, where applicable:

- inspection of electrical installation

- electrical integrity tests, including electrical tests for insulation, earth leakage

- electrical continuity and electrical earthing tests

- inspection of cable pits

- inspection of electrical wiring on cable trays

- inspection of labelling and terminations of electrical wiring

- check type, number and locations of light switches and GPOs

- testing and verification of electrical installation to enable energisation

- verification of protection settings of all protective circuits

- inspection of switchboards

### Pre-commissioning HV electrical activities

HV Electrical equipment checks and testing will include but not limited to the following, where applicable:

- insulation resistance tests

- voltage withstand tests

- Ductor tests

- phase rotation tests

- polarity checks

- primary injection testing of CTs

- secondary injection testing of protection relays

### Pre-commissioning mechanical activities

Mechanical equipment checks and testing will include but not limited to the following, where applicable:

- pipework installations

- valve operations, opening / closing directions

- pump installations

- lifting chains and cable supports

- anchor points

- ventilation system installations

- reservoir mixer installations

- Air valves, PRV installations

- protective coatings

- access ladders

- access hatches and gratings

## Typical Dry-commissioning activities

### Dry-commissioning electrical activities

- Delivery of mechanical, electrical ITPs, FDS and SFAT documentation to IFC status

- Electrical energisation of motor control centres (MCCs) and field instrumentation

- voltage tests

- trip tests

- functional tests

- testing and adjustment of safety devices

- check of ranges/settings of equipment

- Control power redundancy testing.

- Alternative mains power supply testing

- Generator power supply testing

- confirmation of ‘Fail Safe’ mechanisms

- check maintained emergency and exit lights

- check two way switching operation

- check operation of photo-electric cell and override switch

- correct operation of all field connected items

- electrical point to point checks

- Motor starter configuration and tuning

- Motor rotation checks

- Confirmation of ‘Fail Safe’ mechanisms

- correct functionality of all site connected items on each motor drive, including Local Control Station (LCS), Latch/Emergency Stop push button, thermistor, motor anti-condensation heaters, etc.

- set up and programming of VSDs and soft starters

- power redundancy testing

### Dry-commissioning controls and instrumentation activities

Controls and instrumentation equipment checks and testing will include not limited to the following, where applicable:

- download RTU/PLC and SCADA/IICATS software

- network communications verification

- Setting up of flowmeters

- initial configuration and calibration of Field Instrumentation

- instrument configuration in accordance with the IO list, units, ranges etc

- initial configuration of operator set points and alarm values

- checking the electrical instrumentation and control systems input and output signals in conjunction with the RTU/PLC and SCADA/IICATS system

- SCADA/IICATS picture testing and screen navigation

- checking equipment operation and remote lockout from LCS

- calibrate and test all instruments and analysers

- simulate fault condition tests

- check interlocks, RTU/PLC and SCADA/IICATS logic

- alarm handling, including local and SOC Alarms

- Profibus network testing

- Network redundancy testing

- Fibre Optic testing (OTDR)

### Dry-commissioning mechanical activities

Mechanical equipment checks and testing will include not limited to the following, where applicable:

- Air compressor configuration - Setting of Load/Unload setpoints

- rotation checks (bump test) of all pumps and motors

- Pump configuration

- Pump performance tests

- System storage test

- Vibration measurements

- Noise measurements

- Water hammer tests

- Ventilation system performance tests

- Mixer operational testing

- Blower performance testing

- setting of pressure control/pressure sustaining and pulsation dampers

- Anchor points

### Dry-commissioning electrical-mechanical activities

Electro-mechanical and mechanical equipment checks and testing will include but not limited to the following, where applicable:

- runs of rotating equipment, rotating direction, and performance of electric motors

- Valve, actuator, and limit switch configuration

- Initial configuration of PRVs, PCVs and associated hardware

- functional tests of equipment

- testing and adjustment of safety devices

- recording of key test / set points in TAR, (specifically PRVs and pressure vessels)

- check that equipment is correctly lubricated and lubrication reservoirs charged with suitable lubricant

- clearance, end play and operation of major bearings

- level control of pumps

- valve positions and operation

- check of lifting facilities

- control valve operational tests

- Testing of asset including but not limited to all mechanical and electrical equipment, instrumentation, control and SCADA systems, alarm annunciators, set points.

NOTE: The setup is limited to motor nameplate details, motor protection settings and other parameters to enable “bump” testing of the motors.

Records of parameters are to be recorded and supplied prior to testing of any motors.

Cut-over Plan Template

Introduction	26

Project Description	26

Cutover Strategy	27

Sequencing of cutovers	27

Pre inspections and pre work	27

Detailed Methodology	28

Stage 1 – Insert Stage name	28

Stage description & boundaries	28

Stage pre-requisites and input requirements	28

Sequencing	28

Operating arrangement at end of stage	29

Stage supporting deliverables	29

Communication	30

Communication protocols	30

Contact Details	30

Definitions	31

Attachments	31

Ownership	32

Change History	32

# Introduction

Examples have been added and highlighted in yellow – these will need to be removed or updated to suit requirements.

## Project Description

[Do not type here. This is instructional text. Mandatory. Explain briefly the background of the project/activity/upgrade. Keep to a very key and simple description – include the document purpose (is this cutover methodology for a specific phase or full project etc.]

[Enter text]

# Cutover Strategy

[Do not type here. This is instructional text. Mandatory. This section is to detail the staging of cutovers and/or cut-ins. Consider providing a high-level diagram in this header section to articulate how different staging may fit together]

[Enter text]

## Sequencing of cutovers

[Do not type here. This is instructional text.

Mandatory. List the sequence or stages and approximate duration here. The detail of the phases will be contained in later sections]

| Stage/Step | Work Description | Duration | Comments |
| --- | --- | --- | --- |
| 1 | Temporary Pumping Trial | 4 hours | Req |
| 2 | [Activity or Step Description] | [Duration and Units] | [Enter Text] |
| 3 | [Activity or Step Description] | [Duration and Units] | [Enter Text] |
| 4 | [Activity or Step Description] | [Duration and Units] | [Enter Text] |

## Pre inspections and pre work

| Item | Work Description | Comments |
| --- | --- | --- |
| 1 | Cutover Plan/Methodology Meeting |  |
| 2 | Review of Risk and Contingency Plan | Including HIDRA |
| 3 | [Activity Description] | [Enter Text] |
| 4 | [Activity Description] | [Enter Text] |

# Detailed Methodology

## Stage 1 – Insert Stage name

### Stage description & boundaries

[Do not type here. This is instructional text. Mandatory – Provide a brief (one paragraph) description of the stage, and its boundaries. Outline its relationship to commissioning worklots. This entire section will be repeated for each respective stage]

[Enter text]

### Stage pre-requisites and input requirements

[Do not type here. This is instructional text.

Mandatory. States the inputs and/or pre-requisites required for this stage. May include Factory Acceptance testing, completion of previous works or stages etc.

This section must also include any key control system (IICATS/SCADA) Inputs, such as alarm or interlock disabling.

Include details of process requirements including power, flow rates, volumes required.]

| Item | Description | Comments |
| --- | --- | --- |
| 1 | OCR submitted | Submit to xyz. |
| 2 | FIFM | [Enter Text] |
| 3 | [Enter Text] | [Enter Text] |
| 4 | [Enter Text] | [Enter Text] |

### Sequencing

[Do not type here. This is instructional text. Mandatory. Provide a diagram here for the stage – this could be a diagram/sketch of the flow path/power supply/etc arrangement used.]

[Insert Diagram Here]

[Do not type here. This is instructional text. Mandatory. Detail the sequence of activities that need to occur. This should include any temporary systems, shutdowns, submissions to other authorities (Ausgrid etc.), or hold points.] Item; Activity; Relevant assets; Comments. 1; - Establish Temp Generator; - Generator Panel. 2; - [Enter text]; - [Enter text]. 3; - [Enter text]; - [Enter text]. 4; - [Enter text]; - [Enter text].

### Operating arrangement at end of stage

[Do not type here. This is instructional text.

Mandatory Use this section to be clear about what the operating arrangement is for assets at the end of this stage of cutover. Examples are included below]

| Item | Assets | Operating status | Contingency/comments |
| --- | --- | --- | --- |
| 1 | Power Supply- Feeder 1 | Unavailable | Offline |
| 2 | Power Supply- Feeder 2 | Available | Generator Dry Hired for period |
| 3 | Pump 1 | Available - Manual | Requires Operator via Call Out |
| 4 | Pump 2 | Available - Auto | Pump 1 in manual – requires call out |
| 5 | Pump 3 | Unavailable | Offline |
| 6 | [Enter Text] | [Enter Text] | [Enter Text] |

### Stage supporting deliverables

[Do not type here. This is instructional text.

Mandatory. This table should summarise deliverables for the stage, including any documentation for Interim Operations.]

| Item | Document/deliverable | Comments |
| --- | --- | --- |
| 1 | OCR | Submit to xyz. |
| 2 | Interim Operating Procedure | Submit to Ops, Copy onsite. |
| 3 | Marked up Single Line Diagram | Copy onsite |
| 4 | Marked up P&ID | Copy onsite |
| 5 | [Enter Text] | [Enter Text] |

# Communication

## Communication protocols

| Event type | Responsibility |
| --- | --- |
| Operation Failure | ACME Constructions |
| Maintenance – Existing Assets | Sydney Water |
| Maintenance – Upgraded Assets | ACME Constructions |
| Complaints | Sydney Water Project Manager |
| [Enter Text] | [Enter Text] |
| [Enter Text] | [Enter Text] |

## Contact Details

| Description | Contact Details |
| --- | --- |
| Engineering Support and coordination | [Enter Name] [Enter Mobile Number] |
| Construction Project Manager | [Enter Name] [Enter Mobile Number] |
| Mechanical Support | [Enter Name] [Enter Mobile Number] |
| Electrical Support | [Enter Name] [Enter Mobile Number] |
| [Enter Text] | [Enter Name] [Enter Mobile Number] |

# Definitions

[Do not type here. This is instructional text.

Mandatory. Define all key terms and acronyms that are particular to the plan. Do not include terms that are not mentioned in the document.]

| Term | Definition | Source |
| --- | --- | --- |
| [Enter term] | [Enter definition (and further rows as needed)] | [Enter source] |

## Attachments

[Do not type here. This is instructional text.

If relevant, list any attachments to support this plan. This should Include:

-ITP Register

-Commissioning Schedule

-MMD Register

-Commissioning Risk Assessment (but after performing it with stakeholders).]

| Attachment | Title |
| --- | --- |
| 1 | [Enter text] |
| 2 | [Enter text (and further rows as needed)] |

# Ownership

[Do not type here. This is instructional text.

Mandatory. Insert details of the Group that owns the plan as well as the as the position title of owner and author.]

| Role | Title |
| --- | --- |
| Group | [Enter text] |
| Owner | [Enter position title] |
| Author | [Enter name and position title] |

## Change History

| Version | Issue Date | Approved by | Brief description of change and consultation |
| --- | --- | --- | --- |
| V1 | 7/08/2026 | [Enter name and position title] | New document |

- Commissioning Risk Assessment Template

| DATE OF REVIEW |  |  |
| --- | --- | --- |
| Project Number |  |  |
| Project Name |  |  |
| Project Manager |  |  |
| Date of Review |  |  |

| No. | Risk Issue | Causes | Consequences | Risk Owner | Likelihood | Consequence | Risk Rating | Existing Safeguards / Controls | ACTION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Description | Person Responsible | Department | Date Due | Likelihood | Consequence | Risk Rating |
| Temporary Bypass RISK ASSESSMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Failure to maintain clean and clear work areas introducing hazards | Items not stored correctly Congestion work area | Slips, trips and falls |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Contact with sewage/biosolids |  | Disease, Infection, |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Lifting objects manually without assistance | -Opening lids and hatches -Moving equipment and tools | Muscular strain, Injuries to back / legs / arms, pinch injuries |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Bites / Stings by wildlife on site | -Site Walks -Opening Pits / moving equipment -Uncut grass | Bites, stings, injuries |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Exposure to electricity during testing activities | -Equipment Testing -Circuit Testing -Commissioning of Devices | Electric Shock, Fatality |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Field/Manual operation of equipment and Unexpected operations | -Unexpected starting of equipment -Incorrect equipment operates -Noise | -Noise -Unexpected movements -Injuries |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Remote operation of equipment leads to unexpected operations | -Unexpected starting of equipment -Incorrect equipment operates -Noise | -Noise -Unexpected movements -Injuries |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | SSI SCADA Team Commissioning activities and Interfaces | - Impacting on others eg Process, Client or other construction teams - Electrocution - Unauthorised access to SCADA - Uncontrolled Release of Pressure, electricity of liquid - Unexpected equipment operation or starting. - Working out of hours | -Injuries -Equipment Damage -Process Interruptions |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Mishandling of Process Fluids during commissioning | -Commissioning in brownfield areas -Inadequate communication or signage -Regular changing state of site | -Inadvertent operation of equipment -Process Interruptions -Injury -Damage to assets |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Unknown operating status of equipment | -Commissioning in brownfield areas -Inadequate communication or signage -Regular changing state of site | -Inadvertent operation of equipment -Process Interruptions -Injury -Damage to assets |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Add project Specific items during risk assessment workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Monitoring and Measuring Device (MMD) Register Template

| DOCUMENT TITLE | Monitoring and Measuring Devices Register |  |  |
| --- | --- | --- | --- |
| DOCUMENT ID: |  | ASSOCIATED ITP No. |  |
| REVISION DATE |  | WORK LOT No. |  |
| SWC PROJECT NO |  | SITE NO. & NAME |  |
| PROJECT NAME |  | PROJECT MANAGER |  |

| PROJECT MONITORING & MEASURING DEVICE REGISTER |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ASSET No | DEVICE DESCRIPTION | MANUFACTURE | MODEL | SERIAL NUMBER | CALIBRATION DATE | CALIBRATION DUE | Owner | COMMENT |
| Add rows for each device |  |  |  |  |  |  |  |  |

- O&M Manual Template

[Site Street Address] & Insert Site Photo

| SUPPLIER | [Enter Supplier/Contractor Name] |
| --- | --- |
| SUPPLIER CONTRACT NO. | [Enter Supplier’s Contract Reference number] |
| CONTRACT NO. (SYD WATER) | [Enter Sydney Water Contract No. / Specific Task Order No.] |
| ADDRESS | [Enter Supplier Address] |
| PHONE | [Enter Supplier Contact Phone – For Support/ Parts etc.] |
| EMAIL | [Enter Supplier Contact Email – For Support/Parts etc.] |

Description	38

Document Purpose	38

Site / works overall description	38

Sub-system description	38

Technical Data	39

[Facility No.] Description	39

[Asset No.] Description pump	39

[Asset No.] Sump Pump	40

[Asset No.] Description Instrument	40

[Asset No.] Description Lifting Equipment	41

[Asset No.] Penstocks / wet well isolation	41

[Asset No.] Fan	42

[Asset No.] Add others as relevant (RCDs, other equipment etc.)	42

Principles of operation	43

Example subsection – pumping units	43

Operating Instructions	44

Example subsection – Manual SPS Operation	44

Flushing pump 1	44

Installation and commissioning instructions	45

Installation checks	45

Checks before first start	45

Checks after first start	45

Ongoing operational checks	45

Preventative maintenance	46

Qualification of maintenance personnel and warnings	46

Maintenance Schedule	46

[Asset No.] Description	46

Overhaul and major periodic maintenance	47

[Asset No.] Description	47

Test data, inspection results and troubleshooting	48

Test data & inspection results	48

Troubleshooting	48

Parts list and recommended spares	48

Appendices	49

# Description

## Document Purpose

[Enter text]

This manual should be studied carefully and understood prior to the operation of any systems or equipment related to this installation. Incorrect operation can cause personal injury or damage to property and equipment. It is important that this manual be reviewed in conjunction with the relevant Sydney Water safety plans and procedures associated with the operation and maintenance of this installation.

## Site / works overall description

[Enter text]

| Asset No. | Description (Maximo) | Existing / New |
| --- | --- | --- |
| [Enter Asset No.] | [Maximo Description] | Choose an item. |
| [Enter Asset No.] | [Maximo Description] | Choose an item. |
| [Enter Asset No.] | [Maximo Description] | Choose an item. |

## Sub-system description

[Enter text]

# Technical Data

[Enter text]

## [Facility No.] Description

| Characteristic | Detail/Information |
| --- | --- |
| Constructor | Acme Constructions Pty Ltd |
| Relevant General Arrangements | ST00XXX-4090[A] |
| Operation Duty |  |
| Storage Capacity |  |
| Discharge Location |  |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |

## [Asset No.] Description pump

| Characteristic | Detail/Information |
| --- | --- |
| Serial No. |  |
| -[Enter Asset Tag] | [Item Information] |
| -[Enter Asset Tag] | [Item Information] |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |
| Lead Time | [Item Information] |
| Unit Mass (Kg) | [Item Information] |
| Impellor Diameter (mm) | [Item Information] |
| Impellor Type | [Item Information] |
| Duty Flow Rate (L/s) | [Item Information] |
| Duty Pump Speed (rpm) | [Item Information] |
| Duty Head (m) | [Item Information] |
| Duty NPSHR (m abs) | [Item Information] |
| Duty Pump Efficiency (%) | [Item Information] |
| Duty Power Input (kW) | [Item Information] |
| Duty Noise Level (dBA @ 1m) | [Item Information] |
| Upper Bound Flow Rate (L/s) | [Item Information] |
| Upper Bound Pump Speed (rpm) | [Item Information] |
| Upper Bound Head (m) | [Item Information] |
| Upper Bound NPSHR (m abs) | [Item Information] |
| Upper Bound Pump Efficiency (%) | [Item Information] |
| Upper Bound Power Input (kW) | [Item Information] |
| Upper Bound Noise Level (dBA @ 1m) | [Item Information] |
| Lower Bound Flow Rate (L/s) | [Item Information] |
| Lower Bound Pump Speed (rpm) | [Item Information] |
| Lower Bound Head (m) | [Item Information] |
| Lower Bound NPSHR (m abs) | [Item Information] |
| Lower Bound Pump Efficiency (%) | [Item Information] |
| Lower Bound Power Input (kW) | [Item Information] |
| Lower Bound Noise Level (dBA @ 1m) | [Item Information] |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |
| [Enter Descriptor] | [Item Information] |

## [Asset No.] Sump Pump

| Characteristic | Detail/Information |
| --- | --- |
| Serial No. |  |
| -[Enter Asset Tag] | [Item Information] |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |
| Lead Time | [Item Information] |
| Unit Mass (kg) | [Item Information] |
| Flowrate (L/s) | [Item Information] |
| Head (m) | [Item Information] |
| Pump Speed (rpm) | [Item Information] |

## [Asset No.] Description Instrument

| Characteristic | Detail/Information |
| --- | --- |
| Serial No. |  |
| -[Enter Asset Tag] | [Item Information] |
| -[Enter Asset Tag] | [Item Information] |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |
| Lead Time | [Item Information] |
| Measuring Range | [Item Information] |
| Power Supply | [Item Information] |
| Output Signal | [Item Information] |
| Connection size | [Item Information] |
| Ingress Protection (IP) | [Item Information] |
| Sensor Material | [Item Information] |
| Sensor Housing Material | [Item Information] |
| Seal (Type, Material, Size) | [Item Information] |
| Cable Length | [Item Information] |

## [Asset No.] Description Lifting Equipment

| Characteristic | Detail/Information |
| --- | --- |
| Serial No. |  |
| -[Enter Asset Tag] | [Item Information] |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |
| Lead Time | [Item Information] |
| Safe Working Load (SWL) | [Item Information] |
| Operating Speed Bridge (m/min) | [Item Information] |
| Operating Speed Hoist (m/min) | [Item Information] |
| Motor / Current | [Item Information] |

## [Asset No.] Penstocks / wet well isolation

| Characteristic | Detail/Information |
| --- | --- |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |

| Asset No. | Size | Material | Seat/Seal | Description |
| --- | --- | --- | --- | --- |
| PEN01 | DN450 | 316SS | Resilient | Wet Well 1 Inlet Isolation |
| [Item Information] | [Item Information] | [Item Information] | [Item Information] | [Item Information] |

## [Asset No.] Fan

| Characteristic | Detail/Information |
| --- | --- |
| Serial No. |  |
| -[Enter Asset Tag] | [Item Information] |
| Manufacturer | [Item Information] |
| Address and Contact No. | [Item Information] |
| Type | [Item Information] |
| Model No. | [Item Information] |
| Lead Time | [Item Information] |
| Unit Mass (kg) | [Item Information] |
| Flowrate (L/s) | [Item Information] |
| Pressure (Pa) | [Item Information] |
| Fan Speed (rpm) | [Item Information] |

## [Asset No.] Add others as relevant (RCDs, other equipment etc.)

[Enter text]

# Principles of operation

[Enter text]

This site contains specific risks and hazards including;

Trade waste

Noise levels in excess of xxxx

Principles of operation subsection should be generated for each major equipment item and / or sub-system which operates together.

## Example subsection – pumping units

[Enter text]

# Operating Instructions

[Enter text]

## Example subsection – Manual SPS Operation

### Flushing pump 1

# Installation and commissioning instructions

[Enter text]

## Installation checks

| [CHECKLIST PURPOSE] |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | DESCRIPTION OF CHECK | PASS | N/A |
| 1 | [Enter text] | £ | £ |
| 2 | [Enter text] | £ | £ |
| 3 | [Enter text] | £ | £ |
| 4 | [Enter text] | £ | £ |

## Checks before first start

| [CHECKLIST PURPOSE] |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | DESCRIPTION OF CHECK | PASS | N/A |
| 1 | [Enter text] | £ | £ |
| 2 | [Enter text] | £ | £ |
| 3 | [Enter text] | £ | £ |
| 4 | [Enter text] | £ | £ |

## Checks after first start

| [CHECKLIST PURPOSE] |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | DESCRIPTION OF CHECK | PASS | N/A |
| 1 | [Enter text] | £ | £ |
| 2 | [Enter text] | £ | £ |
| 3 | [Enter text] | £ | £ |
| 4 | [Enter text] | £ | £ |

## Ongoing operational checks

| [CHECKLIST PURPOSE] |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | DESCRIPTION OF CHECK | PASS | N/A |
| 1 | [Enter text] | £ | £ |
| 2 | [Enter text] | £ | £ |
| 3 | [Enter text] | £ | £ |
| 4 | [Enter text] | £ | £ |

# Preventative maintenance

## Qualification of maintenance personnel and warnings

Only qualified personnel should work on electrical, plumbing, and mechanical equipment.

Before commencing any maintenance work the pump should be completely disconnected from the mains by a qualified person.

Under continuous running conditions the pump motor housing can become very hot. To prevent burn injury allow to cool down before handling.

Electrical equipment should not be subjected to direct water hose pressure; and indirect splashing should be minimized during plant wash-down and clean up.

When carrying out maintenance activities, personnel should follow the site safety requirements. This should include following FIFM and Lock Out Tag Out procedures and closing of isolation valves. Where possible rain sewage out of the pump volute. Check that the equipment item & surrounding pipework is depressurised before disconnecting it.

Ensure that the appropriate PPE is worn for the task, e.g. goggles/face shield, chemical resistant gloves, etc. Personnel should also ensure that maintenance activities will not adversely affect plant operations.

## Maintenance Schedule

### [Asset No.] Description

| [ITEM DESCRIPTION] |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTIVITY | TASK DESCRIPTION | FREQUENCY | CONSUMABLES | LABOUR HRS |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |

# Overhaul and major periodic maintenance

## [Asset No.] Description

| [ITEM DESCRIPTION] |  |  | [DESIGN LIFE YRS] |  |
| --- | --- | --- | --- | --- |
| ACTIVITY | TASK DESCRIPTION | FREQUENCY | CONSUMABLES | LABOUR HRS |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |

# Test data, inspection results and troubleshooting

## Test data & inspection results

| Asset / Device | Available data | Location stored / Appendix no. |
| --- | --- | --- |
| [Enter text] | - [Enter text] | [Enter text] |
| [Enter text] | - [Enter text] | [Enter text] |

## Troubleshooting

| Problem | Possible causes | Action |
| --- | --- | --- |
| [Enter text] | - [Enter text] | [Enter text] |
|  | - [Enter text] | [Enter text] |
| [Enter text] | - [Enter text] | [Enter text] |
|  | - [Enter text] | [Enter text] |
| [Enter text] | - [Enter text] | [Enter text] |
|  | - [Enter text] | [Enter text] |

## Parts list and recommended spares

| Parent Asset | Equipment Item | Part No. | Supplier | Lead Time (wks) |
| --- | --- | --- | --- | --- |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |
| [Enter text] | [Enter text] | [Enter text] | [Enter text] | [Enter text] |

# Appendices

[Enter text]

| Appendix | Title |
| --- | --- |
| 1 | [Enter text] E.g. OEM manuals for individual equipment |
| 2 | [Enter text (and further rows as needed)] |

# Ownership

## Ownership

| Role | Title |
| --- | --- |
| Group | Engineering Integration |
| Owner | Senior Manager, Engineering Integration |
| Author | Milton Pathirana Widana |

## Change history

| Version No. | Prepared by | Date | Approved by | Issue date |
| --- | --- | --- | --- | --- |
| V1 | M. Bennett | 16/06/2026 | Nima Gorjian, Manager, Engineering Integration | 7/08/2026 |